Closure Document

Executive Summary

GradMatch-AI was initiated to digitize and automate the university placement process, connecting fresh graduates with employers through an AI-powered keyword matching engine. The project was completed within the planned 8-week timeline and budget of 650,000 PKR (actual spend 648,200 PKR)

All core objectives defined in the Project Charter have been met:

- Fully functional web-based system delivered

- Secure authentication (JWT + bcrypt) implemented

- Student and employer profile management operational

- Admin moderation queue (approve/reject) active

- Keyword-based matching engine (Cosine Similarity) deployed

- Email notifications, application tracking, and job bookmarking working

Project Objectives – Final Status

| Objective | Target | Actual | Status |
| --- | --- | --- | --- |
| Complete web-based system within 8 weeks | 8 weeks | 8 weeks | ✅ Achieved |
| Secure login + authentication | JWT + HTTPS | Implemented & tested | ✅ Achieved |
| Student/employer profile management | CRUD complete | 100% working | ✅ Achieved |
| Employer job posting + admin approval | Full workflow | Operational | ✅ Achieved |
| Resume upload (PDF, ≤5MB) + keyword extraction | Working | 98% extraction accuracy | ✅ Achieved |
| Rule-based keyword matching (no deep ML) | Match score 0–100% | Score formula implemented | ✅ Achieved |
| Top 3–5 recommendations per student | ≥3 jobs | Average 4.2 matches/student | ✅ Achieved |
| Response time ≤5 sec | <5 sec | Avg 2.3 sec | ✅ Achieved |
| Test coverage ≥85% | 85% | 92% (unit), 88% (integration) | ✅ Exceeded |

All MUST HAVE requirements (FR-01 through FR-09, NFR-01 through NFR-03) were delivered. Six of the SHOULD HAVE features (FR-10, FR-11, FR-12, FR-14, FR-15, NFR-04) were also completed; the remaining two (FR-13 in-portal messaging, NFR-05 500 concurrent users) were deferred to Phase 2.

Key Deliverables – Final Checklist

| Deliverable | Planned | Actual | Acceptance |
| --- | --- | --- | --- |
| Feasibility Study | Week 1 | Week 1 | Approved |
| Project Charter | Week 1 | Week 1 | Approved |
| Requirements Document | Week 2 | Week 2 | Approved |
| WBS + Gantt/CPM | Week 2 | Week 2 | Approved |
| UI Prototype (Figma) | Week 2 | Week 2 | Approved |
| Database Design (PostgreSQL) | Week 3 | Week 3 | Approved |
| Backend API (FastAPI) | Week 3–5 | Week 5 | Working |
| Frontend | Week 3–5 | Week 5 | Working |
| Matching Engine | Week 6 | Week 6 | Passed QA |
| Admin Dashboard | Week 5 | Week 5 | Approved |
| Final Documentation | Week 8 | Week 8 | Submitted |
| Deployment | Week 8 | Week 8 | Live |

Budget Summary

| Cost Category | Estimated (PKR) | Actual (PKR) | Variance |
| --- | --- | --- | --- |
| Development (Labor) | - | - | - |
| Frontend Developer (2 mo @ 80k) | 160,000 | 160,000 | 0 |
| Backend Developer (2 mo @ 80k) | 160,000 | 160,000 | 0 |
| AI/Python Engineer (2 mo @ 100k) | 200,000 | 200,000 | 0 |
| Project Manager / QA (1.6 PM @ 55k) | 88,000 | 85,000 | -3,000 |
| Infrastructure |  |  |  |
| Domain name (1 year) | 33,500 (Charter) / 4,500 (Cost est) | 4,500 | -29,000 |
| Web hosting (university server free) | 5,000–8,000 | 0 | -5,000 |
| AWS S3 (resume storage – free tier) | 0 | 0 | 0 |
| Email API (SendGrid free tier) | 0 | 0 | 0 |
| Contingency | 37,500 | 38,700 | +1,200 |
| Total | 650,000 | 648,200 | -1,800 |

Risk Management – Closeout Review

| Risk ID | Description | Mitigation Applied | Residual Risk | Status |
| --- | --- | --- | --- | --- |
| R1 | AI matching accuracy <70% | Rule-based first, tested with 50 sample resumes; accuracy reached 82% | Low | Closed |
| R2 | Third-party API failure | No critical external APIs used; email SendGrid had fallback local logging | None | Closed |
| R3 | Performance under 1,000 users | Load testing with 500 simulated users; response time 2.3 sec | Medium (deferred to Phase 2) | Partially closed |
| R4 | Task delays due to academics | Weekly sprint tracking, flexible deadlines; all milestones met | Low | Closed |
| R5 | Data breach (student info) | Encryption, HTTPS, role-based access; no incidents | Low | Closed |

Lessons Learned

What Went Well

- Clear requirements (MoSCoW + validation) – The 11 issues identified during requirements validation (VAL-I01, VAL-C03, etc.) were resolved early, preventing rework in later phases.

- Use of open-source tools – FastAPI, PostgreSQL, and Tailwind kept costs near zero and allowed the team to focus on logic rather than licensing.

- Weekly sprint discipline – The 2-week agile cycles (Jira + Slack) caught the resume-parsing bug, during Week 5, not Week 7.

- COCOMO estimation – The 7.6 person-month effort estimate proved accurate; the actual team of 4 developers delivered exactly on schedule.

What Could Be Improved

- Resume parsing edge cases – Scanned PDFs (images) failed. Added a warning message for users. Fix: Include OCR as a Phase 2 requirement.

- In-portal messaging (FR-13) – Originally a “SHOULD HAVE”, it was removed because the team realized it would require web sockets and real-time DB. Better scoping upfront would have avoided the last-minute descoping.

Metrics Collected

| Metric | Value |
| --- | --- |
| Total lines of code (backend + frontend) | 3,450 LOC (estimate) |
| Number of unit tests | 124 |
| Defects found during QA | 47 (P1: 2, P2: 8, P3: 25, P4: 12) |
| Defects remaining at closure | 0 (P1-P2), 3 (P3-P4, deferred) |
| Average time from bug report to fix (P1) | 3.5 hours |
| User satisfaction | 4.6 / 5 (students), 4.3 / 5 (employers) |

Pending / Deferred Items for Phase 2 & 3

| Feature | Reason for Deferral | Target Phase |
| --- | --- | --- |
| In-portal real-time messaging (FR-13) | WebSocket complexity | Phase 2 |
| Mobile application (Android/iOS) | Out of Phase 1 scope | Phase 2 |
| Advanced ML matching (beyond keyword) | Cost of training data | Phase 3 |
| LinkedIn API integration | Requires paid agreement | Phase 3 |

End of Project Closure Report

This closure document assumes the project was executed exactly according to the previously submitted plans (feasibility, charter, requirements, etc.).