Section 1

JOB PORTAL SYSTEM - WBS Hierarchy

Section 2

PROJECT COST ESTIMATION

1 Project Assumptions:

- Estimated Size: 3 KLOC (3,000 Lines of Code).

- Average Developer Rate: 80,000 PKR per Person-Month (PM).

- Target Timeline: 8 Weeks (2 Months).

- We have selected the Organic Mode, which is standard for small teams working in a familiar domain (web development)

1.1 Effort Calculation: The formula for Organic Mode Effort is E = 2.4 × (KLOC)^1.05.

- E = 2.4 × (3)^1.05

- Total Effort Required: 7.6 Person-Months (PM)

1.2 Team Size Calculation for an 8-Week Timeline: COCOMO's standard duration formula calculates an optimal timeframe of ~5.3 months. To compress this into our strict 8-week (2-month) deadline, we must adjust the team size:

- Formula: Staff = Total Effort / Required Duration

- Calculation: 7.6 PM / 2 Months = 3.8

- Required Team Size: 4 Developers (working concurrently for 8 weeks).

1.3 Total Estimated Development Cost:

- Formula: Cost = Total Effort × Rate per PM

- Calculation: 7.6 PM × 80,000 PKR

- Labor Cost: 608,000 PKR

- Infrastructure & Contingency: 42,000 PKR

- Total Estimated Project Cost (Initial Investment): 650,000 PKR

2. Financial Viability & Business Value

Assumption for Benefits: Automating the manual placement process (printing, screening, calls) saves the university an estimated    8-60,000 PKR per month in operational and administrative overhead (Annual Savings = 720,000 PKR).

2.1 Return on Investment (ROI) - Year 1

ROI demonstrates the percentage of profit generated against the project cost.

- Formula: [(Total Annual Benefit - Total Cost) / Total Cost] × 100

- Calculation: [(720,000 - 650,000) / 650,000] × 100

- Year 1 ROI: +10.7%

- Achieving a positive ROI within the very first year is exceptional for internal software tools.

2.2 Payback Period (Break-Even Point)

This answers the question: "How long until the system pays for itself?"

- Formula: Total Project Cost / Monthly Savings

- Calculation: 650,000 PKR / 60,000 PKR

- Payback Period: 10.8 Months

- The system will completely pay for its own development cost before the end of the next academic year.

2.3 Net Present Value (NPV) - 3 Year Projection

NPV calculates the current value of the future cash savings the system will generate over 3 years, accounting for inflation (using a standard 10% discount rate).

- Formula: NPV = [Sum of Present Value of Cash Flows] - Initial Investment

- Year 1 Savings Present Value: 720,000 / (1.10)^1 = 654,545 PKR

- Year 2 Savings Present Value: 720,000 / (1.10)^2 = 595,041 PKR

- Year 3 Savings Present Value: 720,000 / (1.10)^3 = 540,946 PKR

- Total Present Value (3 Years): 1,790,532 PKR

- Net Present Value (NPV): 1,790,532 - 650,000 = +1,140,532 PKR

2.4 Infrastructure & Software Costs

The project heavily leverages existing university infrastructure and open-source technologies to keep Capital Expenditures near zero.

- Hosting & Database: Utilizing the university's existing Apache server and MySQL database (Constraint CON-03). (Cost: 0 PKR)

- Domain Registration: Securing a local domain (e.g., .edu.pk or .pk) for 1 year. (Cost: ~4,500 PKR)

- Cloud Storage: AWS S3 for storing 5MB PDF resumes. The AWS Free Tier (5GB) covers the initial load of ~1,000 students. (Cost: 0 PKR)

- AI Matching Engine: Utilizing the open-source Python NLP library. (Cost: 0 PKR)

- Email API: SendGrid Free Tier (100 emails/day) for system notifications and verification. (Cost: 0 PKR)

2.5 Human Resource Costs (Labor)

The commercial estimation allocates the 7.6 Person-Months (PM) of effort generated by the COCOMO model across a 4-person development team working concurrently for the strict 2-month (8-week) deadline. Salaries are estimated based on entry-level/junior market rates in Pakistan.

- Frontend Developer (React): 2 months effort @ 80,000 PKR/month = 160,000 PKR

- Backend Developer (Node.js/MySQL): 2 months effort @ 80,000 PKR/month = 160,000 PKR

- AI/Python Engineer: 2 months effort @ 100,000 PKR/month = 200,000 PKR

- Project Manager / QA (Part-time / 1.6 PM): @ 55,000 PKR/month = 88,000 PKR

- Total Labor Cost (Matches COCOMO 1.3): 608,000 PKR

2.6 Contingency & Total Alignment

As calculated in Section 1.3, the remaining budget allocated to reach the 650,000 PKR total includes:

- Infrastructure (Domain Name): 4,500 PKR

- Contingency Buffer (Approx. 6%): 37,500 PKR

- Total Project Investment: 650,000 PKR